## Sheet1
Task | Start | End | Percent Complete | Resources | Notes
Concept exploration prototypes | 2014-10-01 | 2014-11-01 | 100% | Justin,Max | Processing Sketch, OpenSCAD drawings
Website | 2014-10-04 | 2014-10-04 | 100% | Justin | Website changes and blogging ongoing
3D printed screen frame design | 2014-10-04 | 2014-10-04 | 100% | Max
Virtual photo booth app | 2014-11-19 | 2014-11-22 | 100% | Justin
Leter of Intent | 2014-11-27 | 2014-12-17 | 100% | Justin
PCB prototype 1 | 2014-12-01 | 2014-12-16 | 100% | Max
2D concept drawings | 2014-12-03 | 2014-12-03 | 100% | Justin
Single screen prototype | 2014-12-09 | 2014-12-15 | 100% | Max | Prototype works @ 28FPS
Grant Application | 2015-01-05 | 2015-01-16 | 100% | Justin
Announce on NYC Resistor blog | 2015-01-13 | 2015-01-13 | 100% | Justin
3D concept models | 2015-01-14 | 2015-01-14 | 25% | Justin
JPEG Slicer | 2015-01-14 | 2015-01-16 | 100% | Max
PCB prototype 2 | 2015-01-14 | 2015-02-01 | 50% | Max | Will be submitted 1/18
Sixteen screen prototype | 2015-01-16 | 2015-01-29 | 100% | Max | Proven it works, still need to rig up 16 screens
Virtual installation | 2015-01-19 | 2015-02-04 | 5% | Justin
Order 512 LCD screens | 2015-01-31 | 2015-01-31 | 0% | Justin,Max | Find out of we can piggyback on MakerBot suppliers
Finalize BM tickets | 2015-02-04 | 2015-02-18 | 0% | Justin,Max | Disorient DGS or general ticket sales
Order PCBs for first panel prototype | 2015-02-15 | 2015-02-15 | 0% | Justin
Grant Results Due | 2015-02-28 | 2015-03-10 | 0% | BMA
First panel prototype | 2015-03-01 | 2015-03-15 | 0% | Max,Justin
PCB prototype 3 | 2015-03-01 | 2015-03-15 | 0% | Max
3D print screen holders | 2015-03-02 | 2015-03-30 | 0% | Justin,Botfarm | Use MakerBot botfarm
Contact BRC WiFi | 2015-03-12 | 2015-03-12 | 0% | Justin
Contact DirectTV/Hughes | 2015-03-12 | 2015-03-12 | 0% | Justin
Contact Disorient | 2015-03-12 | 2015-03-12 | 0% | Justin
Make travel arrangements | 2015-03-12 | 2015-03-12 | 0% | Justin,Max
Order PCBs for second panel prototype | 2015-03-15 | 2015-03-15 | 0% | Justin
Second panel prototype | 2015-03-15 | 2015-03-31 | 0% | Max,Justin
Laser cut schwag design | 2015-03-30 | 2015-04-03 | 0% | Justin
DIY kit API | 2015-03-30 | 2015-04-03 | 0% | Max
3D print schwag design | 2015-04-06 | 2015-04-10 | 0% | Justin
DIY kit documentation | 2015-04-06 | 2015-04-10 | 0% | Max
Introduction video | 2015-04-13 | 2015-04-17 | 0% | Justin,Max
Kickstarter campaign setup | 2015-04-17 | 2015-05-08 | 0% | Justin,Max
Kickstarter campaign | 2015-05-08 | 2015-06-09 | 0% | Justin
Demo at Interactive Show | 2015-06-06 | 2015-06-06 | 0% | Justin,Max
Finalize build relative to funding | 2015-06-09 | 2015-06-09 | 0% | Max,Justin
Order parts for final build | 2015-06-09 | 2015-06-09 | 0% | Justin,Max
Rework two panel prototypes to final design | 2015-06-09 | 2015-06-16 | 0% | Max,Justin
Purchase container space | 2015-07-09 | 2015-07-09 | 0% | Justin
Volunteer build session 1 | 2015-07-11 | 2015-07-12 | 0% | Justin,Max
Volunteer build session 2 | 2015-07-18 | 2015-07-19 | 0% | Justin,Max
Volunteer build session 3 | 2015-07-25 | 2015-07-26 | 0% | Justin,Max
Volunteer build session 4 | 2015-08-01 | 2015-08-02 | 0% | Justin,Max
Full scale testing | 2015-08-02 | 2015-08-08 | 0% | Max,Justin
Deliver to container | 2015-08-09 | 2015-08-09 | 0% | Justin,Max
Travel to Sacramento | 2015-08-20 | 2015-08-20 | 0% | Justin
RV loadout | 2015-08-25 | 2015-08-25 | 0% | Justin
Travel to BRC | 2015-08-26 | 2015-08-26 | 0% | Justin,Max
Setup camp, get placed | 2015-08-27 | 2015-08-27 | 0% | Justin,Max
On playa build session | 2015-08-28 | 2015-08-30 | 0% | Justin,Max
Burning Man | 2015-08-30 | 2015-09-07 | 0% | Justin,Max
Deconstruct half | 2015-09-06 | 2015-09-06 | 0% | Justin,Max
Deconstruct other half | 2015-09-07 | 2015-09-07 | 0% | Justin,Max
Travel to Sacramento | 2015-09-08 | 2015-09-08 | 0% | Justin
Travel to NYC | 2015-09-10 | 2015-09-10 | 0% | Justin
Container pickup | 2015-09-14 | 2015-09-14 | 0% | Justin,Max
Post burn report | 2015-09-15 | 2015-09-15 | 0% | Justin
Order boards for DIY kits | 2015-09-15 | 2015-09-15 | 0% | Justin,Max
Send out Kickstarter rewards | 2015-10-01 | 2015-10-31 | 0% | Justin,Max